## July Effort
Issues Resolved in the Months of July
Issue | Analsysis and Resolution | Status | Efforts
COAPT DM data not available in Recon front end. | In rave front end configuration was missing for particular fields. Solved from Rave side | Completed | 3 hours
RECON: Duplicate Data issue | The testing team entered the data for a single field in two different places which caused the duplicate data issue. Solved by giving them the KT regarding how to enter the data properly. | Completed | 4 hours
Recon: Absorb IV subject details and XSD precondition field missing in Recon | The particular data fields are mapped in Rave properly like how it is in Prod Url. Data entered in the Rave frontend is correct but is not prrocessed in XML while generation. Error from Medidata side and they are looking into it | Completed | 15 hours
Multiple XML's are sent from RAVE for a single trial in a single day. | RAVE xml generation job was scheduled to run 2 hours a day where in Prod its once a day. Schedule time was changed from RAVE side. | Completed | 2 hours
ClinDART: COAPT Submission report not working. | There was a data entry error which caused this issue. Solved from Rave frontend by entering the data properly | Completed | 3 hours
KT for new fields and triggers mentioned in the new testcase document specified by Medidata |  | Completed | 6 hours
AVAdmin Table documentation for four studies |  | Completed | 2 hours
Daily Call |  |  | 5 x 30 min/day = Total 8 hours
Call on Wednesday excluding daily call once in a week |  |  | 30mins = Total 1.5 hours
Call on Friday excluding daily call ADHOC call |  |  | 4 hours
Ongoing FTP isssue |  | In Progress | 2 hours
Daily Monitoring for FTP loads |  |  | 15mins/day = total = 7 hours
Total hours till now |  |  | 57.5

## August Effort
Efforts for the Months of August
Issue | Analsysis and Resolution | Workaround | Status | Total Efforts | Date
1st week
ClinDart Issue during UAT testing | The Coding Configuration is not available on the AVDEV url, which is why a certain field was missing. That missing field was the reason for failing the ClinDart report. | Solved after the confirmation we got from Phalguni that the issue will be properly documented and the business was fine to proceed with this since it was the dev url. From our side we checked if we had any issue anywhere from our side and found none | Completed | 2 hours | 04/08/2020 - 05/08/2020
Recon Issue during UAT testing | The data was not populating in the RECON frontend as claimed by the UAT team | The Rave and Recon team checked internally and found no errors, only after finishing the daily XML loading job data was supposed to get populated. The UAT team didn't wait for the job to finish and they asked for more fields to map in AVAdmin table which was rejected by Phalguni. | Completed | 2 hours | 04/08/2020 - 05/08/2020
Preparing the Clinical View for the UAT team to check the reports in RAVE | The UAT team identified the Clinical View for COAPT CAS was not present in there and they are unable to run the report for that study | Made the Clinical View for COAPT CAS and the report ran properly | Completed | 2 hours | 2020-05-08
PROD and DEV CRF mismatch | The UAT team pointed that the PROD and DEV CRF versions are not matching and they are not the latest ones. | The UAT team overlooked the CRF version names which clearly mentioned that those are the PROD CRF versions running on AVDEV URL. Prepared a comparison document to make them understand that the CRFs are fine | Completed | 30 mins | 2020-03-08
Sanity Checklist |  | Preared the Sanity Checklist to perform the steps on the GO-Live date | Completed | 2 hours
SI Checklist |  | Preparing the SI Checklist as the part of the ongoing project | In Progress | 4 hours | 04/08/2020 - 07/08/2020
Daily Status Meeting |  |  | Completed | 30 mins | 03/08/2020 - 07/08/2020
Weekly Project Meeting |  |  | Completed | 30 mins | 2020-05-08
Total Hours |  |  |  | 13.5 hours
2nd week
SI Checklist |  | Preparing the SI Checklist as the part of the ongoing project, coordinating with Vidhya, Kani and other teams to get the documents that must be documented in the SI checklist | In Progress | 4 hours | 10/08/2020 - 13/08/2020
PROD User List | Asked by Medidata to prepare the PROD User list to send them the notification regarding the maintenance on the GO-Live weekend | Prepared the PROD User list and shared them back | Completed | 2 hours | 2020-12-08
IV Document for RAVE |  | Checking all the steps mentioned in the IV doc and estimating the time that will be needed to perform the entire steps | Completed | 2 hours | 2020-12-08
Daily Status Meeting |  |  | Completed | 30 mins | 10/08/2020 - 13/08/2020
Weekly Project Meeting |  |  | Completed | 30 mins | 2020-12-08
Total Hours |  |  |  | 9 hours
3rd week
SI Checklist |  | Preparing the SI Checklist as the part of the ongoing project. | In Progress | 5 hours | 16/08/2020 - 21/08/2020
Daily Status Meeting |  |  | Completed | 30 mins | 16/08/2020 - 21/08/2020
Weekly Project Meeting |  |  | Completed | 30 mins | 19/8/2020
Total Hours |  |  |  | 6 hours