## Project Schedule
Project Phase | Sl.No | Task Name | Owner | Actual Date | Revision Date | Completion Date | Status | Comment | Reason for delay
PLANNING | 1 | Kick off | Project team | 2020-06-15 |  | 2020-06-15 | Completed
| 2 | Part 11 Complaince | Abbott | 2020-06-15
| 3 | Provide access for RAVE. | Saikat | 2020-06-15 | 2020-06-24 |  | In-Progress | Bala has shared the ticket. - Lee & Kani will raise & share a ticket. - Sinu has access to RAVE - Saikat will provide access for Kani,Bala and Lee | One resource yet to get Abbott accesss.
| 4 | Provide access for ClinDART and RECON Systems. | Lokeshwari | 2020-06-15 | 2020-06-24 |  | In-Progress | Bala raised ticket ,forward the ticket to Lokeshwari. Kani has to raise the ticket Lee has to raise the ticket sinu has got access | One resource yet to get Abbott accesss.
| 5 | Windchill Access | Project team | 2020-06-15 | 2020-06-24 |  | In-Progress | Bala is going to get access. Sinu is going through training. Lee Ann has to attend trainings.
| 6 | KT on RAVE ,ClinDART and RECON sytems | Saikat & Lokeshwari | 2020-06-18 | 2020-06-22 | 2020-06-24 | In-Progress
| 7 | Update RAVE with latest CRF's for four trials | Saikat | 2020-06-15 | 2020-06-24 | 2020-06-26 | In-Progress | 06/22/2020: Testing team will give the 4th trial name to Saikat 06/23/2020: Testing team shared 1 trial name Saikat updated 1 trial ABSORB ,3 more has to be updated.
| 8 | Project Schedule plan creation for tracking (power steering) | Dhina/Lee Ann | 2020-06-15
| 9 | Confirm Upgrade date (AVDEV) | Medidata | 2020-06-15
| 10 | Enter request for upgrade to Medidata technical team(AVDEV) (2 days) | Medidata | 2020-06-15
| 11 | Maintenance change request creation | Vidhya | 2020-06-18 | 2020-06-18 | 2020-06-18 | Completed
| 12 | Maintenance change request review | Vidhya | 2020-06-19 | 2020-06-22 | 2020-06-19 | In-Progress | 06/19/2020:Had review with BSS & BRM 06/22/2020: Scheduled for review with SQA ,since Abbott had mentioned that review needed from SQA on 06/19/2020 Call.
| 13 | Maintenance change request approval | Vidhya | 2020-06-23 | 2020-06-23
| 14 | Analysis of requirements documents | Testing team | 2020-06-22 | 2020-06-22 | 2020-06-22 | Completed
| 15 | Requirement Specification submission | Vidhya | 2020-06-23 | 2020-06-24 |  |  |  | 06/22/2020:Planned to submit soon after CR review (line item 8)but we have to wait for the line item 9 to complete to execute this step.Reason Being Windchill there is a process after approval only I can create Documents.
| 16 | Requirement Specification Approval | Vidhya | 2020-06-24 | 2020-06-25
| 17 | CIA Update | Sinu/Balamurugan | 2020-06-23 | 2020-06-24
| 18 | CIA Review | Sinu/Balamurugan | 2020-06-24 | 2020-06-25
| 19 | CIA Pre-Approval | Sinu/Balamurugan | 2020-06-25 | 2020-06-26
PLANNING GATE STATUS CHECK: Completion of line items 6 ,9, 12 & 15 ---------------------------> BUILD PHASE
BUILD | 20 | Preparation of Test case (2) (1 day) | Sinu/Balamurugan | 2020-06-23 | 2020-06-25
| 21 | Integration sanity check in AVDEV pre-upgrade(3 days) | Sinu/Balamurugan | 2020-06-24 | 06/29/2020 to 07/01/2020
| 22 | Trouble shoot functional issues while transmit between interfaces (3 Days) | Saikat/Ram | 2020-06-24 | 06/29/2020 to 07/01/2020
| 23 | Review of test cases(2 days) | Sinu/Balamurugan | 2020-06-29 | 07/02/2020 to 07/03/2020
| 24 | Approval of test cases (1 day) | Sinu/Balamurugan | 2020-07-01 | 2020-07-06
| 25 | ISSD draft (1 day) | Vidhya | 2020-06-26 | 2020-06-29
BUILD STATUS CHECK: Completion of line item 24--------------------------->TEST PHASE
TEST | 26 | Preparation of test data in RAVE for pre-upgrade in AVDEV.(2 days) | Testing team | 2020-07-06 | 7/7/2020 to 07/08/2020
| 27 | Trouble shoot issues for test data creation(PRE-UPGRADE)(2 days) | Abbott | 2020-07-06 | 07/09/2020 to 07/10/2020
| 28 | Verify RECON load job(0 days) | Ram | 2020-07-07 | 2020-07-10
| 29 | Execute pre-requisite steps of test case (pre-upgrade)(2 days) | Testing team | 2020-07-08 | 07/10/2020 to 07/11/2020
| 30 | Upgrade AVDEV(12 DAYS) | Medidata | 7/10/2020 to 07/27/2020 | 7/13/2020 to 07/28/2020
| 31 | Integration of RECON VAL.(0.5 day) | Ram | 2020-07-28 | 2020-07-29
| 32 | Verification of RECON integration configuration(0.5 day) | Ram | 2020-07-28 | 2020-07-29
| 33 | Create test data in RAVE for ClinDART and RECON (Post -upgrade) | Testing team | 2020-07-29 | 7/30/2020 to 07/31/2020
| 34 | Trouble shoot issues for test data creation(PRE-UPGRADE)(2days) | Data manager | 2020-07-29 | 7/30/2020 to 07/31/2020
| 35 | Trouble shoot functional issues while transmit between interfaces (2 Days) | Ram | 2020-07-29 | 7/30/2020 to 07/31/2020
| 36 | Verfiy RECON Load job(0 days) | Ram | 2020-07-30 | 2020-07-31
| 37 | Execute Test case(Post upgrade)(3 days) | Testing team | 2020-07-31 | 08/03/2020 to 08/05/2020
| 38 | Review of executed test case(2 days) | Testing team with Abbott | 2020-08-05 | 08/06/2020 to 08/07/2020
| 39 | Approval of executed test case (1 day) | Abbott | 2020-08-07 | 8/7/2020 or 08/10/2020
| 40 | IPDR if applicable(5 days) | Testing team | 2020-07-31 | 7/31/2020 to 08/06/2020
| 41 | Support for any trouble shooting(7 days) | Testing team | 2020-07-31 | 7/31/2020to 08/10/2020
| 42 | Trace Matrix update(1 day) | Testing team | 2020-08-10 | 2020-08-11
| 43 | Trace Matrix update Part 11(1 day) | Testing team with Abbott | 2020-08-10 | 2020-08-11
| 44 | Review RTM (2 Days) | Testing team with Abbott | 2020-08-11 | 8/11/2020 to 08/12/2020
| 45 | Approval RTM(1 Day) | Abbott | 2020-08-13 | 2020-08-13
| 46 | ISSD Review (2 days) | Abbott | 2020-08-10 | 8/10/2020 to 08/11/2020
| 47 | ISSD Approval(1 day) | SQA,Support owner | 2020-08-12 | 2020-08-12
| 48 | Validation system summary /CIA post approval (2 days) | Testing team | 2020-08-19 | 8/19/2020 to 08/20/2020
| 49 | Service Authorization(1 day) | Medidata | 2020-08-21 | 2020-08-21
TEST PHASE STATUS CHECK: Completion of line item 35--------------------------->UAT PHASE
UAT | 50 | UAT Execution(10 days) | Abbott | 2020-07-31 | 2020-07-31
| 51 | UAT sign off/approval(3 days) | Abbott | 2020-08-14 | 2020-08-14
| 52 | Support for any troubleshooting | Saikat /Ram | 2020-07-31 | 2020-07-31
| 53 | Existing Prod environment down time communication(0 days) |  | 2020-08-10 | 2020-08-10
UAT PHASE STATUS CHECK: Completion of line item 48--------------------------->GO -LIVE PHASE
GO-LIVE | 54 | Upgrade of production ,URL released /complete | Medidata | 2020-08-22 | 2020-08-22
| 55 | Business Verification | Abbott | 2020-08-23 | 2020-08-23
| 56 | Production Acceptance Signed | Medidata & Abbott | 2020-08-23 | 2020-08-23
| 57 | Application Go-Live | Abbott | 2020-08-23 | 2020-08-23
Go-Live STATUS CHECK: Completion of line item 57--------------------------->HYPERCARE PHASE
HYPERCARE | 58 | Handover to support | Medidata,CTS PM,CTS Run | 2020-08-24 | 2020-08-25
| 59 | SI Checklist | CTS Developer | 2020-08-24 | 2020-08-25
| 60 | Hyper care | Medidata,CTS PM,CTS Run | 2020-08-24 | 2020-09-04

## SLC Deliverables
Document | Template | Process Owner | System Owner | Technical
Maintenance Change Request | Windchill | BPO | SQA |  | BPO – Mehul Patel
Requirement Specification | BTSQC09.05-AT | BPO | SQA, Primary IT Lead |  | SQA – Annamaria Lambidis
Primary IT Lead – Diann Erskine
Change Impact Analysis (CIA) | Windchill | BPO | SQA |  | Architect – Qihong Hu
OQ | BTSQC09.05-Y |  | SQA | Architect | Support Owner – Sujeesh T K
ISSD | BTSQC09.05-AN |  | SQA, Support Owner
IPDR(If needed) | BTSQC09.05-V |  | SQA,PRIMARY IT Lead
Trace Matrix( Functional Requirements to OQ) | BTSQC09.05-U |  | SQA | Architect

## Project Team -System access
Owner | Status
Lee Ann
Kanimozhi | 1) Access to VM + Abbott email id for Kani after 3 to 4 days. 2) After receiving the ABBOTT ID, she has to work on all system access.
Sinu | 1) Received Access fro RAVE ,ClinDART 2) For RECON and ClinDART, full permission is not given, Sinu had sent an email to Lokeshwari. 3) Windchill- working on training.
Vidhya | Received Windchill access
Balamurugan