## Overview
To be filled at the start of the Transition.
Description |  | Coordinate With | Owner | Comments
Domain | PDA | Build | RUN
Power Steering ID/RFC Number | PD-004837 | Build/PMO | RUN
Change Description | Application Upgrade | Build | RUN
Go live date | 22/08/2020 | Build | RUN
Abbott Build PM Name & email | Narina, Chaithanya <chaithanya.narina@abbott.com> | Build | RUN
Cognizant Build PM & email | Rhoton, Lee Ann <leeann.rhoton@abbott.com> | Build | RUN
Abbott RUN CSM & email | Petersen, Adam <adam.petersen@abbott.com> | RUN | RUN
Cognizant RUN Lead | T K, Sujeesh <sujeesh.thattankandy@abbott.com> | RUN | RUN
New/Existing app | Existing | RUN | RUN
App Name | RAVE | Build | RUN
App SP Id | 753 | Build | RUN
App type (Hosted,COTS,Custom) | C-COTS | Build | RUN
Regulatory needs (FDA/Quality Critical, SOX, Privacy, etc.) | Quality Non- Critical | Build/RUN | RUN
Enhancement/Project size (hrs.) | 1597 | Build | RUN
In case of Enhancement
Has 6000 hr trigger met | No | RUN | RUN
6 Months review completed? | Yes | RUN | RUN
In case of New App
ALM(Application Lifecycle Management) Completed? | Yes | RUN | RUN
TVM(Threat Value Management) Completed? | N/A | RUN | RUN

## Key POC
# | Role | Name | Email | Responsibilities
Job ID 1 | Resource Master | Divy,Mathur | divy.mathur@abbott.com | Resource Master sheet update
Job ID 2 | Access Control | Kannan,Yuvaraj | yuvaraj.kannan@abbott.com | ACL Sheet update
Job ID 3 | SMO | Ramachandar Kondaiah, Rajkumar | rajkumar.ramachandarkondaiah@abbott.com | Foundation Data,ITSM update ,Incident Managers update

## Version History
S No | Change Summary | Version | Signature | Name
1 | Initial Draft | 1 | NL | Navakumar, Lalithkumar
2 | Updated Go-Live date in Overview. Added Hypercare criteria in Service Transition. | 1.1 | NL | Navakumar, Lalithkumar
3 | Updated the checklist to add ALM & TVM criteria. | 1.2 | NL | Navakumar, Lalithkumar
4 | Updated the checklist to add Application Monitoring . | 1.3 | NL | Navakumar, Lalithkumar
5 | Updated checklist to add PoC details for AHB & CMDB | 1.4 | NL | Navakumar, Lalithkumar
6 | Updated Checklist with Key POC ,Access control updates | 1.5 | RI | Rakesh,Iyappan

## Service Transition
Sl. No. | Activity | Description | Exit criteria | Coordinate with | Owner | RAG Status | Current Status | Comments
1 | Resource Readiness | Support resources are onboarded as per requirements with necesaary skill sets to support the application. | Domain leads should confirm that the necessary resources are onboarded and ensure that Resource Master Sheet is updated. | RUN Lead | SI Lead & Domain Lead | Green | Completed
2 | Hypercare | To create and schedule proper hypercare plan, which involves agreeing on length of Hypercare period, issue tracking approach and on hypercare completion/acceptance criteria. | •Acceptance criteria needs to be documented in the Transition to Support plan and agreed to before the go live. •Issues should be tracked in ITSM. •Work with CSM and define criteria. | Build(via CSM) | App PoC & Domain Lead | Amber | In Progress
3 | Access Control | Support team should acquire access to all the appropriate environments. Access requirements should be completed including Admin Accounts / User accounts setup for Run Team before the end of hypercare. | Respective supporting team must confirm once the access is provided and ACL sheet should be updated accordingly. Ensure support teams have required access to support applications and not using any service accounts A dash/ I dash accounts | Application Support Team & RUN Lead. | App PoC | Green | Completed
4 | Source code | Final code versions checked into source code repository with access rights provided to the support team | Deployment Plan document to be shared with final version number of code and location. | Build Team | App PoC | Green | Completed | All source codes are stored in VSS vault
5 | CMDB | To ensure that all the application details such as critical attributes, interfaces, server details and relations to other applications are updated in CMDB accordingly. | Share the CR/Incident number and location as reference. Raise GSD ticket to the queue: BTS-GLBL-APM Administration | Build/RUN | App PoC | Not Set | NA
6 | ALM (Application Lifecycle Management - New Transition) & App Health Data | ALM (Application Lifecycle Management) - Assess application health data and complete assessment. | No transition of RED/Amber status, without approved funding/disposition/remediation plan. Update the ALM parameters in below link. https://abbott.sharepoint.com/teams/crp-spring/AAI/SitePages/Application%20Health.aspx | Build/RUN | App PoC | Green | Completed
7 | TVM (Threat Vulnerability Management - New Transition) | TVM (Threat Vulnerability Management) assessment - Scan for vulnerabilities, disposition new issues with funding alignment from CSM | Scan the vulnerabilities and identify any incremental issues to secure the funding with CSM/Business.Ensure one time remediation cost is included in the support cost. If scan not needed get a confirmation mail from CSM. | RUN/CSM | App PoC | Not Set | NA
8 | SLC Repository | Document the name and location of the SLC repository. | To obtain the name and hyperlink of the repository and to update it in AHB | Build | App PoC | Green | Completed | All the documents are stored in Perforce, M-files and WINDCHILL
9 | Disaster Recovery | Leads must verify with business for a DR Plan, If applicable ensure that a DR Plan has been determined, tested along with Rollback procedure and DR test results are available. | A working DR plan is created and stored in shared repository and updated in AHB. | RUN/CSM | App PoC/Domain Lead | Not Set | NA | Vendor holds the document
10 | Foundation Data | Ensure all information is passed over to SMO so that they are able to route the tickets to correct support team. Project team should prepare a list of Keywords and list of questions that help desk team should ask to assign the ticket to correct queue. | Acknowledgement from SMO team. | SMO | App PoC/Domain Lead | Green | Completed
11 | ITSM Queue Update | If required a new queue has to be created or else the product must be added to an existing Queue | Confirmation for the creation/Updating the queue. | SMO | App PoC/Domain Lead | Not Set | NA | Existing Product
12 | Incident Manager | Incident manger must be identified and relevant information must be shared to incident manager for ticket triaging process along with Application PoC details. | Incident Managers are identified and confirmed by leads. | SMO | App PoC/Domain Lead | Green | Completed
13 | Licensing & Certification | Software License/Subscription model is described, contacts are listed, tracking location, methods are described and renewal dates are included. | •The validity date and license details should be obtained and updated in AHB. • To get the license code and to update in secured document. •The necessary certification details should be obtained in AHB. | RUN Lead | App PoC/Domain Lead | Not Set | NA
14 | User Recertification | User recertification either has been done or it has to be scheduled. | Following to be completed as part of user recertification and should be updated in AHB. •Frequency at which user certification must be done. •Script to pull the user list. | CSM | App PoC/Domain Lead | Green | Completed
15 | Business Stakeholders | All key contacts like IT Service Owner, Business Service Owner, System Owner, Escalation matrix and Distribution List should be identified. | Business Stakeholder, Business Process Owners and other key business SME should be obtained and updated in AHB. | RUN | App PoC/Domain Lead | Green | Completed
16 | Cognizant Stakeholders | Individual key contacts should be identified and informed for respective level of support | Necessary details should be obtained regarding the support team and should be updated in AHB | RUN | App PoC/Domain Lead | Green | Completed
17 | Defect Disposition | All open and known defects are logged. A proper work around is planned for the individual open defects. | Defect list must be updated with proper disposition plan and approved. If a defect tracking tool is not available use the sheet below. | Build | App PoC | Green | Completed | All the defects are logged in FogBugz application
18 | App Inventory /Hopex | Each application along with it's meta data must be included in the application inventory. | App Master must be updated respectively. | CSM & RUN | App PoC/Domain Lead | Green | Completed
19 | Final BSS sign-off | All required ABP's are reviewed and agreed scope are delivered and business has accepted the solution. | Signed 10 B Document. | BRM/RUN | Domain Lead | Amber | In Progress
20 | Automated Monitoring | Use Abbott tools (Autosys/BMC patrol) to perform standard automated monitoring of Software, Database, Servers, Jobs etc for proactive alerting. Ensure correct ITSM group and priority is set for automated alerts. Typically P2 – nothing below that. *Server – disk space, Key services up/down – ITSM High tickets to team. *Software – any key application service that needs to up/run – High ITSM tickets to support group on down failure. *DB – Database standard monitoring and ITSM reporting implemented. | ITSM tickets to Abbott tools and engineering group – implementation confirmation Queue Name to raise GSD: WIP-GLBL-Tools | RUN Team | App PoC | Green | Completed
RAG STATUS SUMMARY
|  |  | Percentage of criteria not evaluated | 25
|  |  | Percentage of criteria in RED | 0
|  |  | Percentage of criteria in AMBER | 10
|  |  | Percentage of criteria in GREEN | 65
CURRENT STATUS SUMMARY
|  |  | Percentage of criteria not started | 0
|  |  | Percentage of criteria being worked at | 10
|  |  | Percentage of criteria completed | 90
Defect Disposition

## Solution Transition
Sl. No. | Phase | Activity driven | Description | Exit criteria | Coordinate with | Owner | RAG Status | Current Status | Comments
1 | KT | Knowledge Transition | KT should be obtained from the development team. | The KT obtained must be documented and should be updated in AHB.The updated KT document and MoM can also be stored in the below mentioned SharePoint Link. | Build/RUN | App PoC | Not Set | NA
2 |  | Training | Support team must complete the necessary trainings with respect to the application and division. | Confirmation from respective support resource and ISO training completion report. | RUN | App PoC | Not Set | NA
3 |  | Code Deployment | KT should be obtained on Code promotion and deployment. | SIQ Document or Deployment Plan document should be shared or the path of SLC repository should be shared. | Build | App PoC | Not Set | NA
4 |  | Reverse KT | Support team must provide the reverse KT to the build team. | Reverse KT sign-off or MoM. | Build/RUN | App PoC | Not Set | NA
5 |  | SMO KT | SMO Process KT including metrics has to be completed. | SMO KT Sign-off or MoM. | Build/SMO | App PoC | Not Set | NA
6 | Documents | User Requirement Specification (URS) & Functional Requirement Specification (FRS) | Requirements, Process and Functional documentation have been drafted/updated as necessary. | Relevant approved document or the SLC repository path. | Build/RUN | App PoC | Green | Completed | Present in Windchill
7 |  | Architecture and Detailed Design Document | Architecture Document/Config Document should be shared to RUN team.E2E design review (process flows, review functional specs, impact assessment) must be completed and documented. | Relevant approved document or the SLC repository path. | Build/RUN | App PoC | Green | Completed | Present in Windchill
8 |  | Unit Test | Unit test document should be updated and shared with support team. | Relevant approved document or the SLC repository path. | Build | App PoC | Not Set | NA
9 |  | Deployment Plan | The deployment process and steps must be documented. | Relevant approved document or the SLC repository path. | Build/Infra | App PoC | Green | Completed | Medidata owns the document
10 |  | Code Review | Project team should have reviewed all the objects that are delivered in the project and code review document should be delivered | Relevant approved document or the SLC repository path. | Build/RUN | App PoC | Not Set | NA
11 |  | Requirement Traceability Matrix (RTM) | All the functionalities must be linked with the test cases and should be documented. | Relevant approved document or the SLC repository path. | Build | App PoC | Green | Completed | Present in Windchill
12 |  | User Acceptance Testing (UAT) | User Acceptance Testing must be completed with all scenarios. | UAT Sign Off must be shared. | Build/RUN | App PoC | Green | Completed | Present in Windchill
13 | Test Logs | Test Protocol | Regression, UAT, Integration testing, Performance testing completed and documented. The defects logged must be shared. | Test Summary with business approval or the SLC repository path. | Build/RUN | App PoC | Green | Completed | Present in Windchill
14 |  | System Testing/Validation Testing | All the scenarios must be tested and recorded. | Test Summary with business approval or the SLC repository path. | Build/RUN | App PoC | Green | Completed | Present in Windchill
15 |  | Performance and Load testing | To perform the Load testing and to document the results. | Relevant approved document or the SLC repository path. | Build | App PoC | Not Set | NA
16 |  | KEDB | All open defects documented in a Known Error Knowledge Article | KA/Defect tracker must be shared. | Build/RUN | App PoC | Green | Completed
17 | AHB Handbook (Send a mail to BTSDocCenter@abbott.com to get the editable format of the AHB) | Database Model | Database model is included or referenced, if applicable | AHB must be updated and routed for approval in M-files. | Build/RUN | App PoC | Green | Completed
18 |  | Infrastructure | All environment (Dev, Test, Staging, Prod, etc.) server names and meta data are listed. Document all software version requirements for layered software (IE10, etc.) | AHB must be updated and routed for approval in M-files. | Build/RUN/Infra | App PoC | Green | Completed
19 |  | McAfee ENS(End Point Security) | To ensure all the servers are installed with McAfee ENS version. | AHB must be updated and routed for approval in M-files. | Build/Infra | App PoC | Green | Completed
20 |  | Layered Software | All infrastructure software used by the system (for all layers of the stack including desktop) including version number and vendor support contact information is documented and referenced | AHB must be updated and routed for approval in M-files. | Build/RUN/Infra | App PoC | Green | Completed
21 |  | Batch Jobs | Are all batch jobs scheduled in tool with correct details and failure alerts. | AHB must be updated and routed for approval in M-files. | Build | App PoC | Not Set | NA
22 |  | Downtime - Planned | Instructions for planning downtime including End User communication instructions including user group names for communication of down time | AHB must be updated and routed for approval in M-files. | Build/RUN/Infra/DB | App PoC | Green | Completed
23 |  | Backup/Restore | Backup/Restore plan completion | AHB must be updated and routed for approval in M-files. | Build | App PoC | Green | Completed
24 | SME Handbook | SME Handbook. | Update the SME handbook based on the following checklist and ensure that all the items are updated in the SME handbook. | Update the SME handbook and should be stored in the share point portal. | RUN | App PoC | Green | Completed
25 | ALM (Application Lifecycle Management - Enhancement) | ALM reassessment- Update and complete - verify and update application health metrics in the centralized repository/in the below link. | No transition of RED/Amber status, without approved funding/disposition/remediation plan | No transition of RED/Amber status, without approved funding/disposition/remediation plan. Update the ALM parameters in below link. https://abbott.sharepoint.com/teams/crp-spring/AAI/SitePages/Application%20Health.aspx | Build/RUN | App PoC | Green | Completed
26 | TVM (Threat Vulnerability Management - Enhancement) | TVM reassessment - rescan for vulnerabilities, disposition of new issues with funding alignment from CSM. | Proper work order is generated for the Remediation work for the incremental vulnerabilities identified | Scan the vulnerabilities and identify any incremental issues to secure the funding with CSM/Business.Ensure one time remediation cost is included in the support cost. If scan not needed get a confirmation mail from CSM. | CSM/RUN | App PoC | Not Set | NA
27 | Release Managemnt Process | It is the responsibility of the build team to follow the release process before moving to the production. | Run team has to ensure that Build team has followed Release Process before going live. | All the release specific documents must be updated and final approval from the release manager must be obtained. Release Manager: Ajoo, Sunil Jones <suniljones.ajoo@abbott.com> | Build | SI Lead | Green | Completed
28 | Automated Monitoring | Use Abbott tools (Autosys/BMC patrol) to perform standard automated monitoring of Software, Database, Servers, Jobs etc – proactive alerting. Ensure correct ITSM group and priority is set for automated alerts. Typically P2. | To check if App Monitoring is in place for the application. | ITSM tickets to Abbott tools and engineering group – implementation confirmation Queue Name to raise GSD: WIP-GLBL-Tools | RUN | App PoC | Green | Completed
RAG STATUS SUMMARY
|  |  |  | Percentage of criteria not evaluated | 38.4615
|  |  |  | Percentage of criteria in RED | 0
|  |  |  | Percentage of criteria in AMBER | 0
|  |  |  | Percentage of criteria in GREEN | 61.5385
CURRENT STATUS SUMMARY
|  |  |  | Percentage of criteria not started | 0
|  |  |  | Percentage of criteria being worked at | 0
|  |  |  | Percentage of criteria completed | 100
SME Handbook Checklist V2.0

## Commercial Finalization
Sl. No. | Activity driven | Description | Exit criteria | Coordinate with | Owner | RAG Status | Current Status | Comments
1 | App type | Whether the app is a Hosted, COTS or Custom | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed | C-COTS
2 | Avg. No. of Incidents / Month | Average number of Incidents logged every month | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed | 10
3 | Avg. No. of SR / Month | Average number of Service Requests logged every month | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed | 2
4 | App regulatory needs | Is the application regulated and which regulations and audit considerations apply. (e.g. FDA/Quality Critical, SOX, Privacy, etc.) | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed | Quality Non-Critical
5 | DBA Efforts | How much DBA effort goes into the app per month | Application Based Pricing (ABP) | RUN Lead | SI Lead | Not Set | NA
6 | App Complexity | Application complexity in terms of Modules, Screens, Interfaces, and customizations. Use H/M/L scale. | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed | M
7 | Geographic Scope | Global user base distribution | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed | Global
8 | No. of users | Number of users | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed | ~3000
9 | Language Support | How many languages the application supports and how many languages support needs to be given in? | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed | 2
10 | Onsite Interaction | Describe the required onsite interaction needed to provide day to day support including the crucial days/times for support | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed | 2 hours
11 | 6000 Hours | Application needs to be verified for 6000 hours breach.(ME)?? | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed
12 | 6 Months | Application must be reviewed every 6 months for ABP parameter. | Application Based Pricing (ABP) | RUN Lead | SI Lead | Green | Completed
RAG STATUS SUMMARY
|  |  | Percentage of criteria not evaluated | 8.3333
|  |  | Percentage of criteria in RED | 0
|  |  | Percentage of criteria in AMBER | 0
|  |  | Percentage of criteria in GREEN | 91.6667
CURRENT STATUS SUMMARY
|  |  | Percentage of criteria not started | 0
|  |  | Percentage of criteria being worked at | 0
|  |  | Percentage of criteria completed | 100

## Defect Disposition
Legend:Use below listed values for the respective field
# | Category | Disposition | Defect ID | Defect description | Defect Source | Workaround | Accepted by Business
S.no | Major | Change request | Unique identifier | Brief summary | Interface | Available | Yes
| Minor | Accepted AS IS | (Manual OR |  | Feature/Functionality | Unknown | No
| Low impact | Needs decision | Defect tracking tool) |  | Data | None | Pending
Cosmetic
Configuration
Performance
# | Category | Disposition | Defect ID | Defect description | Source | Workaround | Accepted by Business

## SME Handbook Checklist V2.0
S.No | Section Number | Document Header | Checklist Description
1 |  | Document Naming Standard | SME handbook naming pattern should be in the format "SPID_ApplicationName_Domain_SME Handbook". (Eg: 4277_PAIRS _MFG_SME Handbook)
2 |  | Application Name in First Page | SPID should be added in the first front page along with the application name and version number. Application Full name should be given in the first front page along with abbreviation
3 |  | First Page Table | All the columns are mandatory
4 |  | Table of Contents Page | Section number should be in sequence and link should be embeded in all the contents.
5 | 1.1 | Purpose | This place should clearly mention the purpose of the document and precisely give an overview regarding the areas that will be covered in this document.
6 | 1.2 | Responsibilities | Include all the roles and responsibilities (like server team, database team, upstream/downstream interfaces and any third party vendor teams, etc) involved in the application. Also include the team DL or ITSM queue name. (Eg: Support team AN_IRM_APPS_SUPPORT@abbott.com).
7 | 1.3 | Definitions and Acronyms | All the acronyms used in the document should be added
8 | 2.1.1 | Business Process Workflow | Application business process workflow architecture should be explained with a clear flow-chart type of diagram and the same should be explained properly in words.
9 | 2.2 | Module Description | All the application modules should be explained in detail with a diagram and the same should be explained properly in words as well.
10 | 2.3 | User Roles & Privileges | • All the columns are mandatory. Type of user roles should be given (Eg. Business Users, BI Architects, Cognos Admin, etc). • In the privileges column, mention what type of privilege the concern user has (Eg: Users have Read & execute access to PAIRS Reports and Packages.Users can create ad hoc in their personal folders using PAIRS Packages). • Mention the security group in the 'Security Group' column (Eg. IT - BI Architect/Developer APP-DL-COGNOS-OA-AN-RptAdm-FrmWrkMgr)
11 | 2.4 | Assumptions, Dependencies & Risks) | All the columns are mandatory and include the details of the server team, database team, upstream, downstream interfaces and any third party vendor teams support team DL or ITSM queue or email id.
12 | 2.6 | Service Requirements | All the columns are Mandatory
13 | 2.7 | Drawbacks / Constraints / Known Issues | Key/Recurring issues (including P1/P2) should be mentioned here with KA numbers or ITSM ticket number
14 | 2.7.1 | P1 & P2 Ticket Details | List down the P1 & P2 ticket details of the application / Refer the high priority ticket details path here
15 | 2.7.2 | Root Cause Analysis (RCA) details | Mention the RCA details of the P1 and P2 tickets / Refer the RCA path here
16 | 2.8 | Key Standard and Ad hoc Service Requests | Details of the key standard and ad hoc service requests should be given here
17 | 2.9 | Key Precautions/Lessons learnt | Mention the key precautions and lessons learnt here
18 | 2.1 | Key Enhancements | Key enhancement details should be given here
19 | 3.1 | Application Architecture | Application architecture should be explained with an architecture diagram
20 | 3.2 | Environment Details | This place should include database server and application server information of all the environments (Production & Lower environments)
21 | 3.3 | Hardware Architecture | Not Mandatory. If the team has the information or able to get the information from CMDB, then the same can be included in the document.
22 | 3.4 | Software Architecture | • Software Architecture should explain the code flow. (Eg: Front end --> Business layer --> Middleware --> Database ---> Interfaces (Upstream / Downstream). • If it is a vendor based application, then try to get the details from vendor or else we can mention a comment "It is a vendor based project so this is not applicable"
23 | 3.5 | Database Model | • Include the application database ER diagram and explain in detail about the ER diagram • If it is a vendor based application, then try to get the details from vendor or else we can mention a comment "It is a vendor based project so this is not applicable"
24 | 4 | System Requirements | Mention the user count, location of users & number of sites users using the applications
25 | 4.1 | User Characteristics | Mention the users active directory group and type of permission they have (Eg: Read Execute Access, Full Access, etc...)
26 | 4.2 | External Interface Specifications | Mention the upstream and downstream interface details
27 | 4.4 | System Recovery Procedures | Explain about the system recovery procedures and it should include server, database, batch jobs & interfaces
28 | 4.5 | Disaster Recovery | Details of the disaster recovery should be given here
29 | 4.6 | Business Continuity Program (BCP) | Business Continuity Program details should be given here
30 | 4.8 | Third Party Components | If any third party product/component (Eg: MKS, Cognos, Metamanager) has been used, then mention the details of those.
31 | 5.3 | User Authentication Scheme | We need to mention, how the application authentication or login validation is done. (Eg: Abbott Network Password Scheme, LDAP authentication)
32 | 5.4 | Scheduled Tasks/Batch Process | Mention the details about the scheduled tasks or the batch jobs. This should also include the frequency in which the job runs. Whether any tools has been used ? (Eg: Autosys). How a job will be revoked when it gets stuck or in case of any job failure that occurs.
33 | 5.5 | Process Flow | Mention the business process flow of the application which should cover the end to end business flow.
34 | 5.6 | Program Flow | This should explain the code flow of the application and it should cover the complete flow that includes interfaces as well.
35 | 5.7 | Data Flow | This data flow should explain that from which upstream the application gets the data and to which downstream the application pushes the data.
36 | 5.8 | Folder Structure | Mention the folder structure of the application source code in the source code repository
37 | 5.9 | Configuration Information | Information about the configuration regarding database, LDAP, server, etc… should be mentioned here.
38 | 5.1 | Application Interfaces | Mention the details of all the interfaces that has been used in the application
39 | 5.11 | Application Repository | Give the details of the application document repository, source code repository, etc…
40 | 6.1 | Custom Frameworks | Mention about the Abbott specific customized frameworks if there is any. (Eg: WAF)
34 | 6.2 | Client/Cognizant team information | Provide the details of the client information (application BRM & CSM) and cognizant support team information (Database, Server, third party vendor details, upstream and downstream information)
35 | 6.3 | Development & Build Utilities | Mention the details of the development framework and build utilities(Eg: Eclipse)
36 | 7.1.1 | Application Level Training | Details of application level training required to get the application access
37 | 7.1.2 | Application Access & Onboarding | Give the details on how to get an application access (includes all the user roles)
38 | 7.2 | Support Schedule | Mention the support schedule information which should include the time zone
39 | 7.3 | Application Build & Deployment Strategy | Application build code promotion details should be given here. (Eg: MKS Code Promotion)
40 | 7.6 | Coding Standards | If your application maintains any coding standard, then mention that here.
41 | 7.7 | Stakeholder Communication | Document the stakeholder communication details
42 | 7.8 | Escalation Matrix | Escalation matrix of Cognizant and Abbott should be given
43 | 7.9 | Existing Support Process | Give the details of the existing ITSM ticket support process.
44 | 7.11 | Frequently Occuring Issues & Remedies | Recurring issues should be mentioned here with the KA numbers or the ITSM ticket number
45 | 7.11.3 | Vendor Support Contact Details | Mention the vendor support contact details.
46 | 7.12 | User Management and Recertification | Give the details of the user management roles and their responsibilities (Eg: Global Access Administration Team ---> Validates the user list of active/inactive users.
47 | 8 | Application Dependency Matrix | Mention the details of all the support team informations (Database, Server, third party vendor details, upstream and downstream information)
48 | 9 | References | Details of the reference documents should be mentioned here.
49 | 10 | Change Log | Details of the document version numbers with the information about the one who initially created and the modifications that were done after that in this document.